## EventTasks
Issue | Issue description | Priority | Status
Arrange keynote from VP of People | Confirm VP Angela Torres for 10-minute welcome remarks. Get talking points and AV needs. | Critical | Blocked
Arrange parking and shuttle | Coordinate overflow parking at the church lot across the street. Book a shuttle van for 2 round trips. | Low | In progress
Book lawn games and inflatables | Reserve cornhole sets, giant Jenga, and bounce house from FunTime Rentals. Confirm delivery and pickup times. | Normal | New
Book photographer | Hire a photographer for 3 hours of event coverage. Need candid shots and group photo. Check if Jessica from Marketing can do it. | Normal | In progress
Book venue for Summer Picnic | Reserve the outdoor pavilion at Riverside Park for 200 attendees. Need covered area with access to restrooms and parking. | High | Blocked
Confirm catering headcount | Finalize headcount with BBQ vendor (Smoky Joes). Need vegetarian and gluten-free options for approx 30 attendees. | Critical | Blocked
Confirm food truck arrival time | Follow up with Smoky Joes to confirm arrival by 10am for setup. They need access to a power outlet. | Normal | New
Create event day run-of-show | Draft a minute-by-minute schedule for event day: setup at 8am, guests arrive 11am, remarks at noon, cleanup by 4pm. | Normal | New
Get certificate of insurance for venue | Venue requires COI from our insurance provider. Contact Risk Management to request and submit to Riverside Park office. | High | In progress
Order company-branded t-shirts | Order 200 t-shirts with Summer Picnic 2026 design. Sizes based on RSVP form responses. Use approved vendor PrintCo. | Normal | New
Order custom event banner | Design and print a 6ft vinyl banner with Summer Picnic branding. Coordinate with Marketing for logo files. | Normal | New
Order sunscreen and first aid kits | Purchase 50 sunscreen packets and 3 first aid kits for outdoor event. Check with Office Manager for supplier. | Low | In progress
Print directional signage | Design and print 10 directional signs for parking, entrance, food, games, and restrooms. Use weather-resistant material. | Low | In progress
Recruit day-of volunteers | Identify and confirm 8 volunteers for setup, registration table, games, and cleanup shifts. | Normal | New
Rent portable speakers and microphone | Contact AV Express for outdoor speaker rental. Need wireless mic for emcee and music playback from playlist. | Normal | New
Review vendor contracts | Review and sign contracts for catering, AV rental, inflatables, and photographer. Ensure cancellation terms are acceptable. | High | In progress
Send final reminder email | Send a reminder email 3 days before the event with schedule, parking info, what to bring, and weather contingency plan. | Normal | New
Send save-the-date email | Draft and send company-wide save-the-date for Summer Picnic on June 14. Include location and parking info. | Normal | Completed
Set up RSVP form | Create a Microsoft Forms RSVP with name, dietary restrictions, plus-one, and t-shirt size. Share link in save-the-date. | Normal | Completed
Submit budget approval request | Compile cost estimates from all vendors and submit total budget (,500) to Finance for VP approval. | Critical | Completed